## Gantt_Chart
CS614 Gen AI with LLMs — Project Sprint & Visual Gantt Timeline
16-Day Sprint (18 Oct 2026 - 3 Nov 2026 Presentation Day) ¦ 5-Member Team Allocation & Checkpoints
WBS | Task / Deliverable Name | Owner(s) | System / Phase | 18 Oct | 19 Oct | 20 Oct | 21 Oct | 22 Oct | 23 Oct | 24 Oct | 25 Oct | 26 Oct | 27 Oct | 28 Oct | 29 Oct | 30 Oct | 31 Oct | 1 Nov | 2 Nov | 3 Nov
1.1 | Sanity Evaluation of 10-K Ingested Chunks | Amanda, Xavier | Phase 1 Data | bar: 18 Oct to 19 Oct
1.2 | Freeze Clean Processed Chunks (chunks.jsonl) | Amanda, Xavier | Phase 1 Data | bar: 19 Oct
1.3 | Ingest FinQA & TAT-QA Evaluation Datasets | Member 5 | Evaluation | bar: 18 Oct to 20 Oct
2.1 | Build System A: Naive Dense Vector Search (Chroma) | Amanda | System A (Baseline) | bar: 20 Oct to 23 Oct
2.2 | Build System B: BM25 Lexical + Cross-Encoder Reranker | Xavier, Member 5 | System B (Advanced) | bar: 20 Oct to 24 Oct
2.3 | Build System C: LangGraph State Machine & Decomposer | Anish (Me), Aryan | System C (Adaptive) | bar: 20 Oct to 24 Oct
2.4 | Build System C: Sufficiency Critic & Reflection Loop | Anish (Me) | System C (Adaptive) | bar: 21 Oct to 24 Oct
2.5 | Build System C: Inline Table Citation Mapper & Prompts | Aryan | System C (Adaptive) | bar: 21 Oct to 24 Oct
M1 | ★ MILESTONE 1: Team Sync — Demos & Go/No-Go | All 5 Members | Milestone | bar: 25 Oct
3.1 | Ablation 1: Adaptive vs. Fixed 3-Hop Dynamics | Anish (Me) | Research Study | bar: 26 Oct to 29 Oct
3.2 | Ablation 2: Tabular Chunking (Markdown vs JSON) | Xavier | Research Study | bar: 26 Oct to 29 Oct
3.3 | Ablation 3: Hybrid Alpha & Reranker Context Cliff | Xavier, Member 5 | Research Study | bar: 26 Oct to 29 Oct
3.4 | Ablation 4: Guardrail Interception on Adversarial Qs | Aryan | Research Study | bar: 26 Oct to 29 Oct
3.5 | Ablation 5: Master 100-Q Batch Eval & Pareto Curves | Member 5 | Research Study | bar: 26 Oct to 29 Oct
4.1 | Draft Report: Sec 1 (Motivation) & Sec 2 (Baseline) | Amanda | 10-Page Report | bar: 25 Oct to 30 Oct
4.2 | Draft Report: Sec 3 (Ingestion) & Sec 4 (Architecture) | Xavier, Anish | 10-Page Report | bar: 25 Oct to 30 Oct
4.3 | Draft Report: Sec 5 (Guardrails) & Sec 6 (Results/Pareto) | Aryan, Member 5 | 10-Page Report | bar: 25 Oct to 30 Oct
4.4 | Build Presentation Slides (Deck + Diagrams) | Aryan, Anish | Presentation PPT | bar: 25 Oct to 31 Oct
4.5 | Build Streamlit Live Demo Interface (app.py) | Anish, Member 5 | Working Demo | bar: 28 Oct to 31 Oct
4.6 | Consolidate 10-Page Report Draft & Internal Review | All 5 Members | 10-Page Report | bar: 30 Oct to 1 Nov
4.7 | Slide Rehearsal & Code Repo Packaging (Seeds/README) | All 5 Members | Presentation PPT | bar: 1 Nov to 2 Nov
M2 | ★ FINAL PRESENTATION & REPORT SUBMISSION DAY | All 5 Members | Final Milestone | bar: 3 Nov

## Member_Allocation
CS614 — Detailed Member Role & Workload Allocation
Member Name | Core RAG System Focus | Key Engineering Tasks | Master's Ablation Study | Report Section Ownership
Amanda | System A (Naive Baseline) & Phase 1 Data | Run 1-day sanity eval on 10-Ks; build single-pass Chroma dense search pipeline. | Baseline Context Recall Failure Analysis on Multi-Hop Queries. | Report Sec 1 (Motivation) & Sec 2 (Baseline Architecture)
Xavier | System B (Advanced Single-Pass) & Phase 1 Data | Freeze clean chunks.jsonl; build BM25 index & cross-encoder reranker integration. | Tabular Chunking Ablation: Flat Text vs Markdown vs JSON key-values. | Report Sec 3 (Document Ingestion & Preprocessing)
Anish (Me) | System C (Adaptive Multi-Hop) & Orchestration | Design LangGraph execution DAG; build Query Decomposer & Sufficiency Critic node. | Adaptive vs Fixed 3-Hop Dynamics: Noise drift & early-stopping rates. | Report Sec 4 (State Machine & Multi-Hop Architecture)
Aryan | System C (Adaptive Multi-Hop) & Guardrails | Sub-query generation prompts; inline table citation mapping; adversarial guardrail. | Factual Grounding & Hallucination Defense under Adversarial Disclosures. | Report Sec 5 (Guardrail Defense) & Slide Deck Lead
Member 5 | System B (Hybrid Search) & Evaluation Lead | Hybrid alpha blender; automated RAGAS batch harness; execution latency/cost telemetry. | Inference Economics & Model Tiering: Llama-3.1-8B vs GPT-4o Pareto curves. | Report Sec 6 (Evaluation Results, Pareto Frontier & Cost)