## Gantt_Chart
CS614 Gen AI with LLMs — Project Sprint & Visual Gantt Timeline
16-Day Sprint (18 Oct 2026 - 3 Nov 2026 Presentation Day) ¦ 5-Member Team Allocation & Checkpoints
[11 empty] | Sunday | [6 empty] | Sunday | Mon | Tuesday
WBS | Task / Deliverable Name | Owner(s) | System / Phase | 18 Oct | 19 Oct | 20 Oct | 21 Oct | 22 Oct | 23 Oct | 24 Oct | 25 Oct | 26 Oct | 27 Oct | 28 Oct | 29 Oct | 30 Oct | 31 Oct | 1 Nov | 2 Nov | 3 Nov
1.1 | Sanity Evaluation of 10-K Ingested Chunks | Amanda, Xavier | Phase 1 Data | bar: 18 Oct to 19 Oct
1.2 | Freeze Clean Processed Chunks (chunks.jsonl) | Amanda, Xavier | Phase 1 Data | bar: 19 Oct
1.3 | Ingest FinQA & TAT-QA Evaluation Datasets | Member 5 | Evaluation | bar: 18 Oct to 20 Oct
2.1 | Build System A: Naive Dense Vector Search (Chroma) | Amanda | System A (Baseline) | bar: 20 Oct to 23 Oct
2.2 | Build System B: BM25 Lexical + Cross-Encoder Reranker | Xavier, Kevin | System B (Advanced) | bar: 20 Oct to 24 Oct
2.3 | Build System C: LangGraph State Machine & Decomposer | Anish, Aryan | System C (Adaptive) | bar: 20 Oct to 24 Oct
2.4 | Build System C: Sufficiency Critic & Reflection Loop | Anish, Aryan | System C (Adaptive) | bar: 21 Oct to 24 Oct
2.5 | Build System C: Inline Table Citation Mapper & Prompts | Anish, Aryan | System C (Adaptive) | bar: 21 Oct to 24 Oct
M1 | ★ MILESTONE 1: Team Sync — Demos & Go/No-Go | All 5 Members | Milestone | bar: Sunday 25 Oct
3.1 | RQ1 | Xavier, Amanda | Research Study 1 | bar: Sunday 26 Oct to Sunday 29 Oct
3.2 | RQ2 | Kevin, Aryan | Research Study 2 | bar: Sunday 26 Oct to Sunday 29 Oct
3.3 | RQ3 | Anish | Research Study 3 | bar: Sunday 26 Oct to Sunday 29 Oct
3.4 | Preparation of Golden Dataset | Amanda | bar: 21 Oct to 24 Oct
4.1 | Draft Report - Skeleton - Motivation/PS/RQs | Anish | 10-Page Report | bar: Sunday 25 Oct to Sunday 29 Oct
3.4 | Adaptive MH v2 - Improvements + RQ | Anish, Amanda, Aryan | v2 RAG | bar: Sunday 27 Oct to Sunday 30 Oct
4.2 | Build Presentation Slides (Deck + Diagrams) | Amanda | Presentation PPT | bar: Sunday 29 Oct to Sunday 1 Nov
4.3 | Build Streamlit Live Demo Interface (app.py) | Xavier, Kevin | Working Demo | bar: Sunday 28 Oct to Sunday 31 Oct
4.4 | Consolidate 10-Page Report Draft & Internal Review | Xavier, Kevin | 10-Page Report | bar: Sunday 30 Oct to Sunday 1 Nov
4.5 | Slide Rehearsal & Code Repo Packaging (Seeds/README) | All 5 Members | Presentation PPT | bar: Sunday 1 Nov
M2 | ★ FINAL PRESENTATION & REPORT SUBMISSION DAY | All 5 Members | Final Milestone | bar: Tuesday 3 Nov

## Research_Questions
CS614 — Research Question to Evaluation Metric Mapping
Direct mapping of core research hypotheses to empirical evaluation metrics and expected scientific proofs
Research Question (The 'Why') | Evaluation Metric (The 'Proof') | What It Proves / Expected Scientific Outcome
RQ1: Retrieval Completeness Does iterative multi-hop retrieval successfully gather scattered clues across non-adjacent SEC 10-K sections (MD&A, Market Risk, and Statement Footnotes)? | • Multi-Hop Evidence Recall@k • Context Precision (RAGAS) • Hop-by-Hop Retrieval Attribution | Proves whether System C (Adaptive Multi-Hop) successfully captures distant intermediate clues where single-pass baselines (System A & B) suffer from zero-recall on dependent hops.
RQ2: Factual Faithfulness & Safety Does verifying evidence before generation prevent hallucinations and enforce strict citation grounding in high-stakes financial disclosures? | • RAGAS Faithfulness Score • Citation Precision & F1 • Numerical Grounding Error Rate (Exact-match on dollar amounts / percentages) | Proves whether the Evidence Sufficiency Critic and active hallucination guardrails stop the LLM from generating ungrounded financial figures or fabricating assumptions.
RQ3: Inference Economics & Cost What is the operational cost and latency penalty incurred by running multi-stage agentic loops compared to single-pass systems? | • End-to-End Latency (p50, p90, p99 wall-clock seconds) • Token Consumption per Query (Input & Output) • Estimated Cost ($ / 1k queries) • Pareto Frontier Curve (Faithfulness vs. Cost/Latency) | Quantifies the real-world deployment trade-off: proves whether the accuracy gains of System C justify the 2x–3x higher token consumption and latency overhead over single-pass RAG.

## Member_Allocation
CS614 — Detailed Member Role & Workload Allocation
Member Name | Core RAG System Focus | Key Engineering Tasks | Master's Ablation Study | Report Section Ownership
Amanda | System A (Naive Baseline) & Phase 1 Data | Run 1-day sanity eval on 10-Ks; build single-pass Chroma dense search pipeline. | Baseline Context Recall Failure Analysis on Multi-Hop Queries. | Report Sec 1 (Motivation) & Sec 2 (Baseline Architecture)
Xavier | System B (Advanced Single-Pass) & Phase 1 Data | Freeze clean chunks.jsonl; build BM25 index & cross-encoder reranker integration. | Tabular Chunking Ablation: Flat Text vs Markdown vs JSON key-values. | Report Sec 3 (Document Ingestion & Preprocessing)
Anish (Me) | System C (Adaptive Multi-Hop) & Orchestration | Design LangGraph execution DAG; build Query Decomposer & Sufficiency Critic node. | Adaptive vs Fixed 3-Hop Dynamics: Noise drift & early-stopping rates. | Report Sec 4 (State Machine & Multi-Hop Architecture)
Aryan | System C (Adaptive Multi-Hop) & Guardrails | Sub-query generation prompts; inline table citation mapping; adversarial guardrail. | Factual Grounding & Hallucination Defense under Adversarial Disclosures. | Report Sec 5 (Guardrail Defense) & Slide Deck Lead
Member 5 | System B (Hybrid Search) & Evaluation Lead | Hybrid alpha blender; automated RAGAS batch harness; execution latency/cost telemetry. | Inference Economics & Model Tiering: Llama-3.1-8B vs GPT-4o Pareto curves. | Report Sec 6 (Evaluation Results, Pareto Frontier & Cost)